## Project schedule
| VISIONLATEX | [5 empty] | Project start: | [7 empty] | 2024-03-16
[7 empty] | Display week: | [7 empty] | 1
[7 empty] | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01 | [6 empty] | 2024-04-08 | [6 empty] | 2024-04-15 | [6 empty] | 2024-04-22 | [6 empty] | 2024-04-29
| TASK | Revisited | PROGRESS | START | END | time axis 2024-03-11 to 2024-05-05
 | time axis 2024-03-11 to 2024-05-05
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Set UP team
| Set up version control (Git, GitHub y sync) |  | 60% | 2024-03-16 | 2024-03-16 | 1 | bar: 2024-03-15 to 2024-03-18
| Application |  | 50% | 2024-03-16 | 2024-03-16 | bar: 2024-03-15 to 2024-03-18
| Research Computer Vision algorithms and LaTeX generation tools | https://github.com/AprendizajeProfundo/Diplomado-Avanzado?tab=readme-ov-file#visi%C3%B3n-artificial | 0% | 2024-03-16 | 2024-03-18 | 3
| Finalize project plan and define milestones |  | 0% | 2024-03-18 | 2024-03-22 | 5
| Server y enviroment |  | 0%
| Set up development environment (Python, libraries) |  | 0% | 2024-03-22 | 2024-03-27 | 6
| Datos |  | 0%
| Collect diverse dataset of screenshots for training |  | 0% | 2024-03-17 | 2024-03-19 | 3
Desing
| Preprocess data (resizing, cropping, noise reduction) |  | 0% | 2024-03-18 | 2024-03-22 | 5
| Implement baseline OCR model (e.g.,opencv, Tesseract) |  | 0% | 2024-03-20 | 2024-03-25 | 6
| Experiment with deep learning architectures |  | 0% | 2024-03-25 | 2024-03-28 | 4
| Fine-tune pre-trained models on collected dataset |  | 0% | 2024-03-25 | 2024-03-27 | 3
| Research LaTeX syntax and formatting rules |  | 0% | 2024-03-27 | 2024-03-29
| Develop script to convert extracted text to LaTeX markup |  | 0% | 2024-03-29 | 2024-03-31
| Identify risks |  | 0% | 2024-03-29 | 2024-04-01 | 4
Execution
| Integrate OCR module with LaTeX generation module |  | 0% | 2024-03-31 | 2024-04-05 | 6
| Design user interface for application |  | 0% | 2024-04-06 | 2024-04-10 | 5
| Implement frontend using chosen framework (e.g., PyQt) |  | 0% | 2024-04-11 | 2024-04-15
| Add functionality for image upload and processing |  | 0% | 2024-04-16 | 2024-04-20
| Write unit tests to validate individual components |  | 0% | 2024-04-21 | 2024-04-25
| Perform integration testing to ensure seamless interaction |  | 0% | 2024-04-30 | 2024-05-05 | 6
| Provide updates |  | 0% | 2024-05-10 | 2024-05-14 | 5
| Testing and validation |  | 0% | 2024-05-19 | 2024-05-23 | 5
Evaluation
| Gather feedback from early users or beta testers |  | 0% | 2024-04-02 | 2024-04-05 | 4
| Iterate on application based on feedback |  | 0% | 2024-04-05 | 2024-04-09 | 5
| Prepare for deployment (local server, cloud hosting) |  | 0% | 2024-04-10 | 2024-04-13 | 4
| Deploy application on chosen platform |  | 0% | 2024-04-07 | 2024-04-10 | 4
| Conduct post-deployment testing and troubleshooting |  | 0% | 2024-04-09 | 2024-04-14 | 6
Insert new rows ABOVE this one

## SKELETON Applicacion
DEF FUNCION
latex
|  |  | ESCRIBO CON TABLE | GENERA CODIGO latec
| resultado | PDF
JUPYTER
WORD
imágenes |  | SHINY

## Additional
Week | Main Activities | Additional Activities
1 | Research OCR algorithms and LaTeX generation tools | Set up version control (Git)
2 | Finalize project plan and define milestones | Schedule bi-weekly code review sessions
3 | Set up development environment (Python, libraries) | Allocate time for learning sessions (Python basics, relevant libraries)
4 | Collect diverse dataset of screenshots for training | Develop backup system for project files and data
5 | Preprocess data (resizing, cropping, noise reduction) | Engage with relevant developer communities (forums, online groups)
6 | Implement baseline OCR model (e.g., Tesseract) | Conduct usability testing with initial prototype
7 | Experiment with deep learning architectures | Schedule feedback sessions with potential users
8 | Fine-tune pre-trained models on collected dataset | Iterate on application based on user feedback
9 | Research LaTeX syntax and formatting rules | Optimize application performance and efficiency
10 | Develop script to convert extracted text to LaTeX markup | Document code and project progress
11 | Integrate OCR module with LaTeX generation module | Prepare user documentation and guides
12 | Design user interface for application | Generate API documentation for developers
13 | Implement frontend using chosen framework (e.g., PyQt) | Schedule regular maintenance and updates
14 | Add functionality for image upload and processing | Conduct security audit and implement necessary measures
15 | Write unit tests to validate individual components | Allocate time for continued learning and skill development
16 | Perform integration testing to ensure seamless interaction | Maintain communication and collaboration with team members and stakeholders
17 | Conduct user acceptance testing (UAT) | Review and analyze project progress and adjust timelines or resources as needed
18 | Gather feedback from early users or beta testers | Monitor and manage project risks and uncertainties
19 | Iterate on application based on feedback | Celebrate milestones and achievements
20 | Prepare for deployment (local server, cloud hosting) | Reflect on lessons learned and identify areas for improvement
21 | Deploy application on chosen platform
22 | Conduct post-deployment testing and troubleshooting